Members:
Alex Davis
Steve Kosovich
Tim Leikam
Greg Martini
Pluvali Timline (Updated)
Tim
10/30-11/11
Make sure everything is okay
 with client's database
Greg
10/30-11/11
Make sure scenario editor page is working
Alex
11/11
Admin Views
Greg
11/11
Make sure all pages link together properly
Greg
11/11
Play Game Page
Steve
11/11
Link Login Page to database
Tim
11/11
Store Page
All team plus Debi, client, and three others
11/12-11/21
Testing
All team members
11/13
Project Management Review
All team members
11/14
Client Review
All team members
11/18
Next Semester planning
All team members
11/20
Prototype Demo
All team members
12/2
Client Review
All team members
12/2
Video
All team members
12/2
Poster
Steve
12/11
Documentation
All team members
12/12
Final Prototype Deployed
November
December
Time