Members:
Alex Davis
Steve Kosovich
Tim Leikam
Greg Martini
Pluvali Timline
Tim
10/30-11/11
Make sure everything is okay
 with client's database
All team plus Debi, clients, and three others
11/24- 12/8
Testing
All team members
11/13
Project Management Review
All team members
11/14
Client Review
Greg
10/30-11/11
Make sure scenario editor page is working
All team members
12/12
Final Prototype Deployed
Alex
11/18
Next Semester planning
Alex
11/11
Admin Views
All team members
11/20
Prototype Demo
Steve
12/11
Documentation
Greg
11/11
Make sure all pages link together properly
All team members
12/2
Client Review
Greg
11/11
Play Game Page
Tim
12/9
Video
Steve
11/11
Link Login Page to database
Greg
12/9
Poster
Tim
11/11
Store Page
November
December
Last revision: December 2, 2014