## Sheet1
Team Pluvali - Spring 2015 Timeline
[13 empty] | Alex Davis |  |  | Debra Parcheta
[13 empty] | Steve Kosovich |  |  | Katie Taliercio
Tim Leikam
Greg Martini
Task: |  |  |  | Duration of Task and Who is Responsible
Requirements Revision | Team
Semester Timeline | Team
Documentation |  | Team
Database Refinement |  | Greg
Database View Update |  |  |  |  | Greg and Tim
Scenario/Game Page Fixes |  |  | Greg
Store Page Finalization |  | Tim
Player Page Implementation |  |  | Greg and Tim
Scenario Editor Implementation |  | Alex
Home and Help Page Fixing |  | Steve
Image Button Implementation | [6 empty] | Steve
Text Consistency | [7 empty] | Steve
Refine Site and Inconsistencies | [8 empty] | Team
Test Cycle One | [8 empty] | Team
Test Refinement | [10 empty] | Team
Debug | [10 empty] | Team
Test Cycle Two | [12 empty] | Team
Final Refinement | [14 empty] | Team
Debug | [14 empty] | Team
Video | [14 empty] | Greg and Alex
Poster | [14 empty] | Steve and Tim
Final Presentation | [16 empty] | Team
Deployment | [16 empty] | Team
Week of: | 2015-01-19 | 2015-01-26 | 2015-02-02 | 2015-02-09 | 2015-02-16 | 2015-02-23 | 2015-03-02 | 2015-03-09 | 2015-03-16 | 2015-03-23 | 2015-03-30 | 2015-04-06 | 2015-04-13 | 2015-04-20 | 2015-04-27 | 2015-05-04 | 2015-05-11